## Sheet1
| Document | Infrastructure Standardization
| Author | Wasif Zaman
| Version | 1
| Date of Last Modification | 2014-12-29
Task # | Task Name | Comment | Action | Date
1 | Distribute Test Template to Staff | Create/Update Test Template and distribute to all CTS staff for suggestions | CTS
This process can consist of multiple iterations of template
2 | Create New Infrastructure Documents | Create new infrastructure documents and fill in all the information | CTS
Rename existing infrastructure documents into Infrastructure - Depreciated Gather suggestions from staff Members should make changes as needed to their documents
3 | Move depreciated documents | Move all depreciated documents to archives | CTS
4 | Post-deployment | Continue to gather suggestions from staff | CTS
If the infrastructures become non-standardized after a time, deploy a plan to standardize again